## IP_OptimalCrossing
A3
Title: Finding optimal number of parents, crosses and progeny | Name(s): Kanju Edward | Date:12/05/2020
Background: | Proposed Countermeasure(s):
What is the business reason for choosing this issue? Too few parents will be impossible to maintain adequate diversity required to increase genetic gain over time | Your proposal to reach the future state, the target condition. - What alternatives could be considered? . No alternatives - How will you choose among the options? What decision criteria? .
Current Conditions:
Where things stand today. - What’s the problem with that, with where we stand? We currently use only four parents and only twelve crosses . - What is the actual symptom that the business feels that requires action? We have observed low heritability for quantitative traits like yield Show visually – pareto charts, graphs, drawings, maps, etc.
Implementation Plan:
A chart or table that shows actions/outcomes, timeline and responsibilities. SEE NEXT SHEET + RACI + Performance-Monitoring plan + Matemathical tools
Target(s)/Goal(s)
The specific outcome required for the business. - What is the specific change you want to accomplish now? Increase heritabilty and thus genetic gains by Incresing the number of parents and number of crosses - How will you measure success? When we have incresed the number of progenitors and crosses to the minimum advocated by QG theories is reflected in increased heritability and higher rates of genetic gain for the traits specified in our product profile.
Analysis
The root cause(s) of the problem. - Why are we experiencing the symptom? 1) Very few varieties are resistant to both CMD and CBSD ; 2)Quarantine issues for importing vegatative materials ; - What constraints prevent us from the goal? 1) We need to determine the optimal number of founders and crosses to maximize genetic gain; 2) skills to implement this, . Choose the simplest problem-solving tool for this issue: - 5 Whys - Fishbone - QC Tools - LSS Tools
Follow Up:
Remaining issues that can be anticipated. - Any failure modes to watch out for? Any unintended consequences? Ensure ongoing P-D-C-A (plan-do-check-adjust). Don't stop with implementation.

## Plan_optimal_crossing_etc
Improvement |  |  |  |  | Control
Action item | Responsible | Accountable | Consulted | Informed | KPI | Due date (mm/dd/yyyy) | Baseline (current value) | Target (target value) | Data source (how will it be measured)
Simulate the optimal number of parents, crosses and progeny per cross. to recommend the optimal evaluation strategy that allows to maximize genetic gain per dollar invested | Chris | Eduardo | Edward | Head of breeding, DDG-Research | Number of parents and crosses determined | 2020-07-01 | 4 parents; 12 crosses | TBD | simulated data
Organize a meeting to discuss results from simulation and take a decision on how to run the program | Eduardo | Peter Kulakow | Edward, Chris, Dorcus | Head of breeding, DDG-Research | Meeting ocurring | 2020-07-07 | meeting has not ocurred | Meeting occurs and decision is taken | Results from simulation
Document the new procedure | Edward | Head of breeding | EiB-Roslin | Head of breeding, DDG-Research | SOP developed | 2020-07-30 | SOP has not been developed | SOP will be available | Simulation results and Breeder's experience
Train the technicians on the new SOP | Edward | Head of breeding | Peter Kulakow | Head of breeding, DDG-Research | Training happening | 2020-08-15 | Technicians not trained | Technicians trained | Simulation results and Breeder's experience
Make new crossing block using the new SOP | Technicians | Edward | Peter Kulakow | Head of breeding, DDG-Research | Crossing block using new SOP | 2020-09-01 | Crossing block not established | Crossing block established and technicians using the new SOP | Breeder's experience

## Simulation treatments
Plan 1: Optimal #Parents, #Crosses, #progeny
T1 | Use of current #parentes, #crosses, #progeny
T2 | Different combinations of #parents, #crosses, #progeny under 1500-5000 genotype restriction

## IP_ReducingCycleTime
A3
Title: Reducing cycle time based on QG principles | Name(s): Kanju Edward | Date:12/05/2020
Background: | Proposed Countermeasure(s):
What is the business reason for choosing this issue? By reducing the cycle time we can increase the genetic gain and the likelihood to delivery better products at faster rate increasing our impact and increasing performance. | Your proposal to reach the future state, the target condition. - What alternatives could be considered? Recycling after the first yield evaluation by trading accuracy off. Testing at earlier stages and using sparse testing to cover better the TPE. - How will you choose among the options? What decision criteria? we will go from the least to the most disruptive.
Current Conditions:
Where things stand today. - What’s the problem with that, with where we stand? We currently evaluate our genotypes in two stages of yield trials (preliminary and advanced) before we recycle individuals to ensure high accuracy of selections. - What is the actual symptom that the business feels that requires action? We have a low rate of genetic gain for yield due to long recycling times mainly due to annual cropping cycle (12 months) and low multiplication rate through clonal propagation (1:5). Show visually – pareto charts, graphs, drawings, maps, etc.
Implementation Plan:
A chart or table that shows actions/outcomes, timeline and responsibilities. SEE NEXT SHEET + RACI + Performance-Monitoring plan + Matemathical tools
Target(s)/Goal(s)
The specific outcome required for the business. - What is the specific change you want to accomplish now? Reduce the cycle time in our breeding program for example by going to multi-locational testing early. - How will you measure success? When we have decreased our recycle time to 1-3 years for population improvement and is reflected in higher rates of genetic gain for the traits specified in our product profile.
Analysis
The root cause(s) of the problem. - Why are we experiencing the symptom? 1) low multiplication ratio; 2) long cropping cycle; - What constraints prevent us from the goal? 1) We need to determine the accuracy of selecting parents at the early testing stages; 2) the optimal set of replications and environments needed to maximize genetic gain; 3) skills to implement this, buy-in from the programs, etc. Choose the simplest problem-solving tool for this issue: - 5 Whys - Fishbone - QC Tools - LSS Tools
Follow Up:
Remaining issues that can be anticipated. - Any failure modes to watch out for? Any unintended consequences? There's risk for breeders and management to not seeing the value. Ensure ongoing P-D-C-A (plan-do-check-adjust). Don't stop with implementation.

## Plan_Cycle Time
Improvement |  |  |  |  | Control
Action item | Responsible | Accountable | Consulted | Informed | KPI | Due date (mm/dd/yyyy) | Baseline (current value) | Target (target value) | Data source (how will it be measured)
Simulations to show the trade off in accelerated genetic gain when CET recycle is done as against at PYTstage. Show by simulation how selection of families can result in sustained genetic gain over aperiod than selectng individuals of best performance. Genetic gain to be made at TPEs identified from simulations Can we show through simulation what would be the gain in accuracy and genetic gain when reducing replication within environments to go to more environments under different levels of GxE in the TPE? Implies change in experimental design (i.e. from alpha to augmented or use of sparse testing | Chris | Dorcus | Elizabeth, Afolabi, Dr Kanju | Peter Kulakow | genetic gain from simulation available and report | 2020-07-15 | TBD | TBD | Simulations
Discuss the results of the simulations | Chris | Dorcus | Elizabeth, Afolabi, Dr Kanju | Peter Kulakow | Meeting ocurring | 2020-07-21 | meeting has not ocurred | meeting and decision taken | Results from the simulation
Discuss within the HarvestPlus team and other breeders on the scheme to pilot | Elizabeth, Afolabi, Kanju | Kulakow, Asiedu | HarvestPlus Breeders and team | DDG | Meeting ocurring | 2020-07-30 | meeting has not ocurred | meeting and decision taken | Results from the simulation
During COVID-19 identify strategy to deploy all rapid mutiplication schemes to raise planting materials for the trial | Elizabeth Mercy | Kulakow | Mercy | DDG | sufficent planting materials of elite selected clones multiplied for planting across TPEs | 2020-09-30 | 20 stems each | TBD | report on available stems
Develop a protocol for the new evaluation strategy | Elizabeth Mercy | Kulakow | EiB |  | Protocol available
Run a trianing for the people or NARs to adopt the new SOP | Elizabeth Mercy | Kulakow | EiB |  | SOP available
Run the new evaluation strategy | Elizabeth Mercy | Kulakow | EiB |  |  | 6/1/2020 ¦ 6/1/2021
Present results of GG for early recycle in CBU and PAM on what the new strategy is | Elizabeth ,Afolabi Kanju | Kulakow | Robert Asiedu Kulakow | DDG | present GG for key traits assessed and shared | yet to be decided | yet to be decided | TBD | Reported advanced tria results presented at PAM
Present findings in genetic gain after three cycles during the product advancement meeting and conclude on following the tested scheme | Elizabeth ,Afolabi Kanju | Head of Breeding | Robert Asiedu, Kulakow | DDG | Heritability Accuracy and Genetic Gain | yet to be decided | yet to be decided | TBD | Reported advanced tria results presented at PAM

## SimulationTreatments
Plan 2: | Evaluation/cycle time
Given that we already know that a mixed crossing block from PYT and AYT is the best, can we delay these till the software is ready to test the diffrence btn 1*4 and 4*1 (locs*reps)
Under better TPE sampling at early stages
T1 | Recycling at PYT with 4*1 or 1*4 (locs*rep)
T2 | Recycling at AYT with 6*1 or 2*3 (locs*rep)
T3 | Recycling at UYT-1 with 6*1 or 2*3 (locs * rep)
T4 | Recycling at UYT-2 with 9*1 or 3*3 (locs * rep)
Summary from results in IP1
nParents 16-32
nCrosses 100-200
nProgeny 10-15
Using 19 parents